## Project Timeline
IMPORTANT ABE30 DATES
TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE
2018-01-07 | 2018 Annual Meeting Starts | 15 | 1
2018-01-11 | 2018 Annual Meeting Finishes | -5 | 1
2018-01-31 | Final 2018 Paper Publication Decisions Due to TRB | 10 | 1
2018-03-01 | Submit Triennial Strategic Plan (TSP) | -10 | 1
2018-04-19 | Call for Papers Proposal Site Opens to Public | 5 | 1
2018-05-01 | Call for Papers Site Opens to Public | -10 | 1
2018-06-01 | Paper Submission Site Opens to Public | 20 | 1
2018-06-15 | Workshop Proposals Due | -15 | 1
2018-07-31 | Workshops selected by TRB | -20 | 1
2018-08-01 | All Papers Due to TRB | 5 | 1
2018-08-08 | TRB Assigns Papers to Committees | -5 | 1
2018-08-11 | Paper Reviews Assigned to Members | 15 | 1
2018-09-15 | Paper reviews due | 20 | 1
2018-10-01 | Review Paper Reviews and Record Decisions | -10 | 1
2018-10-01 | Annual Meeting Sessions Finalized, Information Due to TRB | -20 | 1
2018-10-15 | Send Paper Review Decisions to Authors | 5 | 1
2018-11-01 | Authors Begin to Resubmit Papers to TRB | 15 | 1
2018-12-15 | Deadline for chairs to notify staff of any special room AV needs | -15 | 1
2019-01-13 | 2019 Annual Meeting Starts | 20 | 1
2019-01-17 | 2019 Annual Meeting Finishes | -5 | 1
2019-02-01 | Final 2019 Paper Publication Decisions Due to TRB, Authors Notified | 10 | 1